## Active Orders
SL No. | KI ID | Order Received | Region | City | Circuit ID | Order Number | Customer Name | Customer Contact | BW | LOS Performed | LOS Status | LOS ID | CWO Date | Installation Start Date | Installation Complete Date | Delivery Date | Order Status | Assigned To
1 | KIC-001-MW-MEL-STC | 2026-07-02 | CENTRAL | QASSIM | QASSIM-RIYADH DIAS11003 | I14977452579171 | Fosam Limited Company | ابتسام اليامي - 553584472 | 20MBPs | 2026-07-05 | CLOS | 601-22-000 | 2026-07-13 |  |  |  | Under MW Installation | Haroon
2 | KIC-002-MW-MEL-STC | 2026-07-02 | CENTRAL | RIYADHDST | RIYADHDST-RIYADH DIAS11019 | I14977108106221 | Bunyan for Industry CompanySole Partnership | وليد الغامدي - 565577234 | 25MBPs | 2026-07-05 | CLOS | ZAKA160 | 2026-07-13 | 2026-07-23 | 2026-07-25 | 2026-07-25 | Delivered /CR Pending | Haroon
3 | KIC-003-MW-MEL-STC | 2026-07-08 | CENTRAL | RIYADHDST | RIYADHDST-RIYADH DIAS11048 | I14978406074781 | MINISTRY OF ISLAMIC AFFAIRS1 | mutlatq mutlatq- 554141990 | 6MBPs | 2026-07-09 | CLOS | ZTMA001 | 2026-07-19 | 2026-07-25 | 2026-07-26 | 2026-07-26 | Delivered | Shukoor
4 | KIC-004-MW-MEL-STC | 2026-07-08 | CENTRAL | QASSIM | QASSIM-RIYADH DIAS11007 | I14978403932431 | MINISTRY OF ISLAMIC AFFAIRS1 | mutlatq mutlatq- 554141990/+966561733000فواز الوتيد دوام | 6MBPs | 2026-07-13 | CLOS | ZBRA012 | 2026-07-27 |  |  |  | Under MW Installation | Haroon
5 | KIC-005-MW-MEL-STC | 2026-07-10 | CENTRAL | QASSIM | QASSIM-RIYADH W-DIA64771 | I-154546342-0886 | NOURNET ISP 1 | Atif Ahmad - 966504164527 | 8MBPs | 2026-07-13 | CLOS | ZBDA012 |  |  |  |  | Under Activation
6 | KIC-006-MW-MEL-STC | 2026-07-12 | CENTRAL | RIYADHDST | RIYADHDISTRICTS-RIYADH W-DIA64993 | I-154915203-2128 | NOURNET ISP 1 | Atif Ahmad - 966504164527 | 4MBPs | 2026-07-13 | CLOS | ZDAA055 |  |  |  |  | Under Activation
7 | KIC-007-MW-MEL-STC | 2026-07-12 | CENTRAL | RIYADHDST | RIYADHDISTRICTS-RIYADH W-DIA64472 | I-154001313-9084 | NOURNET ISP 1 | Atif Ahmad - 966504164527 | 8MBPs | 2026-07-13 | CLOS | ZTMA001 |  |  |  |  | Under TWAL Approval
8 | KIC-008-MW-MEL-Mobily | 2026-07-21 | CENTRAL | RIYADH | SIP Link 1-274297070922 | 1001274298017320 | Life Care Medical Complex مجمع لايف كير الطبي | 0573240869 منهاز | 1MBPs | 2026-07-21 | CLOS | C6406 | 2026-07-23 | 2026-07-23 | 2026-07-23 |  | Pending Due to Ip issues at Mobily End | Haroon
9 | KIC-009-MW-MEL-STC | 2026-07-16 | CENTRAL | RIYADHDST | RIYADHDISTRICTS-RIYADH W-DIA65540 | I-155313238-4448 | NOURNET ISP 1 | Atif Ahmad - 966504164527 | 8MBPs | 2026-07-20 | CLOS | ZAKA013 |  |  |  |  | Under TWAL Approval
10 | KIC-010-MW-MEL-STC | 2026-06-03 | CENTRAL | RIYADH | RIYADH-RIYADH W-PLL62209 | I-150409923-1673 | TAWAL | Muhanned Abusummah-- 0502897276 | 100Mbps |  | CLOS | ZR4020 |  | 2026-07-20 | 2026-07-20 | 2026-07-20 | Delivered / CR Pending | Haroon
11 | KIC-011-MW-MEL-STC | 2026-06-03 | CENTRAL | RIYADH | RIYADH-RIYADH W-PLL61594 | I-149425327-9129 | TAWAL | Abdulrahman Balfaqih-- 0502897276 | 100Mbps |  | CLOS | ZAKA953 |  | 2026-07-23 |  |  | Under MW Installation / Pending Due to Permission Letter | Haroon
12 | KIC-012-MW-MEL-STC | 2026-06-03 | CENTRAL | RIYADHDST | RIYADHDISTRICTS-RIYADH W-PLL61621 | I-149433405-9386 | TAWAL | Abdulrahman Balfaqih-- 0502897276 | 100Mbps |  | CLOS | FRB04 |  | 2026-07-17 | 2026-07-20 | 2026-07-24 | Delivered / CR Pending | Haroon
13 | KIC-013-MW-MEL-STC | 2026-06-04 | EAST | ALAHSA | ALAHSA-DAMMAM W-PLL60851 | I-148474460-6471 | TAWAL | Muhanned Abusummah-- 0502897276 | 100Mbps |  | CLOS | FRD12 |  |  |  |  | Under MW Installation
14 | KIC-014-MW-MEL-STC | 2026-07-19 | CENTRAL | RIYADHDST | RIYADHDISTRICTS-RIYADH W-DIA65578 | I-155424122-6722 | NOURNET ISP 1 | Atif--0504164527 | 8MBPS | 2026-07-20 | CLOS | FTR16 |  |  |  |  | Under TWAL Approval
15 | KIC-015-MW-MEL-STC | 2026-07-19 | CENTRAL | RIYADHDST | RIYADHDISTRICTS-RIYADH W-DIA65586 | I-155428046-6760 | NOURNET ISP 1 | Atif--0504164527 | 8MBPS | 2026-07-20 | CLOS | FTR14 |  |  |  |  | Under TWAL Approval
16 | KIC-016-MW-MEL-STC | 2026-07-26 | CENTRAL | QASSIM | QASSIM-RIYADH W-DIA66191 | I-155826101-8176 | NOURNET ISP 1 - NOURNET ISP - SC 1 | Atif--0504164527 | 8MBPS |  |  | 689-00-101
17 | KIC-017-MW-MEL-STC | 2026-07-26 | CENTRAL | HAIL | HAIL-RIYADH W-DIA66171 | I-155792125-7075 | NOURNET ISP 1 - NOURNET ISP - SC 1 | Atif--0504164527 | 8MBPS |  |  | ZHAA035

## Cancelled Orders
SL No. | KI ID | Region | City | Circuit ID | Order Number | Customer Name | Customer Contact | BW | LOS Status | LOS ID | Order Received | LOS Performed | CWO Date | Installation Start Date | Installation Complete Date | Delivery Date | Order Status | Assigned To
1 | KIC-018-MW-MEL-STC | CENTRAL | RIYADH | RIYADH-RIYADH W-DIA65391 | I-155156872-9273 | NOURNET ISP 1 | Atif Ahmad - 966504164527 | 8MBPs | CLOS | ZAKA013 | 2026-07-16 | 2026-07-20 |  |  |  |  | Cancelled

## Summary
KI ORDERS — SUMMARY DASHBOARD
Live snapshot — all figures below recalculate automatically from the Sheet1 order log
TOTAL ORDERS |  | LOS COMPLETED (CLOS) | IN PROCESS / INSTALLING |  | AWAITING TWAL APPROVAL | BROWN CONDITION FLAGGED | STATUS NOT YET SET | CANCELLED ORDERS | DELIVERED | GRAND TOTAL (ALL ORDERS)
17 |  | 15 | 3 |  | 4 | 0 | 2 | 1 | 4 | 18
Order Status Breakdown |  |  | Region Breakdown
Order Status | Count | Share | Region | Count
Under Activation | 2 | 13.33% | CENTRAL | 16
Under TWAL Approval | 4 | 26.67% | EAST | 1
In Process | 0 | 0% | Not Specified | 0
Under MW Installation | 3 | 20%
Under MW Installation- Brown Condition | 0 | 0% | Cancelled Orders Summary
Not Yet Set | 2 | 13.33% | Metric | Count
Delivered | 4 | 26.67% | Total Cancelled Orders | 1
Total | 15 | 100%
City Breakdown |  |  | LOS Status Breakdown
City | Count |  | LOS Status | Count
RIYADHDST | 8 |  | CLOS | 15
QASSIM | 4 |  | Pending | 0
RIYADH | 3 |  | Not Started | 2
ALAHSA | 1
Not Specified | 0
Bandwidth (BW) Distribution
Bandwidth | Count
100Mbps | 4
25MBPs | 1
20MBPs | 1
8MBPs | 7
6MBPs | 2
4MBPs | 1
Not Specified | 0
STC vs Mobily Breakdown
Provider | Source Sheet | Count
STC Orders | Active Orders | 16
STC Orders | Cancelled Orders | 1
Mobily Orders | Active Orders | 1
Mobily Orders | Cancelled Orders | 0
Total STC Orders |  | 17
Total Mobily Orders |  | 1
Active vs Cancelled
Status | Count
Active Orders | 17
Cancelled Orders | 1
Grand Total | 18